## Sheet1
Recommendations and management action plans
Recommendations | Priority | Status | Comment | Responsibility | Timeframe
(Recommendation accepted / not accepted)
A1. We recommend that the Association establish a documented IT Security Policy that is tailored specifically to the control environment operating within the organisation. |  | Accepted | We have begun work on producing a draft policy to include auditor recommendations in conjunction with ITMS. | W McCreight | 2026-05-01
2
A2. We recommend that all staff members are required to sign and confirm that they have read and understood the IT Security Policy (once established) and the Association’s IT acceptable use policies. |  | Accepted | When draft policy is approved, all staff will sign policy. | W McCreight | 2026-05-01
This will be included in our induction pack for any new employees.
3
Recommendations | Priority | Status | Comment | Responsibility | Timeframe
(Recommendation accepted / not accepted)
B1. We recommend that the Association reconsider the need for penetration test on the Association’s network to be completed and whether penetration testing takes place in a scheduled manner in future years. Best practice suggests this level of testing should take place annually. |  | Accepted | Penetration test quote received FARC to consider cost/benefit analysis. | W McCreight | 2026-04-01
2
Recommendations | Priority | Status | Comment | Responsibility | Timeframe
(Recommendation accepted / not accepted)
C1. We recommend that the Association conduct a cost-benefit analysis of implementing a Mobile Device Management solution to enable more effective centralised control over company mobile devices. |  | ? | Software costs to be collated to conduct cost benefit analysis. | W McCreight | 2026-05-01
3
Recommendations | Priority | Status | Comment | Responsibility | Timeframe
(Recommendation accepted / not accepted)
D1. We recommend that the Association update the Financial Procedures Manual to include the procedures in place for setting up new suppliers on the online banking system and when approving amendments to existing supplier or staff member’s bank details. |  | Accepted | Financial procedures manual to be updated to reflect Supplier Approval process and sign off checklist. | W McCreight | 2026-06-01
3
Recommendations | Priority | Status | Comment | Responsibility | Timeframe
(Recommendation accepted / not accepted)
E1. We recommend the Association: |  |  | Platform based on-line training has been identified and booked for staff. Awaiting board approval to book training for board members. | K Harper | 2026-07-01
a) provide structured IT cybersecurity training to all staff and Board members (the use of a centralised e-learning platform may be the most efficient approach in this respect); | 2 | Accepted
b) ensure that once operational, training completion rates are monitored and follow up action taken for instances where training is not completed by the communicated deadline; and |  |  | Monthly review of completed training. Follow up emails to learners, report progress/completion of training to FARC.
c) introduce the use of phishing simulations within the organisation with a view to enhancing staff awareness in this respect and to identify any further training needs. Third party support may be needed in this regard.
|  | Accepted | Collate quotes from third party providers and schedule of testing throughout the year. | K Harper | 2026-09-01
2026-07-01
|  | Accepted |  | K Harper

## Sheet2
| Recommendation | Priority | Comment | Responsible | Original | Revised
[5 empty] | Timeframe | Timeframe
1 | A1. We recommend that the Association establish a documented IT Security Policy that is tailored specifically to the control environment operating within the organisation. | 2 | We have begun work on producing a draft policy to include auditor recommendations in conjunction with ITMS. | WMcC/KH | 2026-05-01 | 2026-11-04
2 | A2. We recommend that all staff members are required to sign and confirm that they have read and understood the IT Security Policy (once established) and the Association’s IT acceptable use policies. |  | When draft policy is approved, all staff will sign policy.
|  | 3 |  | WMcC | 2026-05-01 | 2026-11-04
This will be included in our induction pack for any new employees.
3 | B1. We recommend that the Association reconsider the need for penetration test on the Association’s network to be completed and whether penetration testing takes place in a scheduled manner in future years. Best practice suggests this level of testing should take place annually.
|  | 2 | Penetration test quote received FARC to consider cost/benefit analysis. | WMcC/KH | 2026-04-01 | Cttee agreed to undertake test.
[6 empty] | 2026-11-04 | Est Cost £2,862
4 | C1. We recommend that the Association conduct a cost-benefit analysis of implementing a Mobile Device Management solution to enable more effective centralised control over company mobile devices. | 3 | Software costs to be collated to conduct cost benefit analysis. | WMcC/KH | 2026-05-01 | Initial analysis suggest
this would not be
cost efficient. Agreed
not to proceed.
5 | D1. We recommend that the Association update the Financial Procedures Manual to include the procedures in place for setting up new suppliers on the online banking system and when approving amendments to existing supplier or staff member’s bank details. | 3 | Financial procedures manual to be updated to reflect Supplier Approval process and sign off checklist. | WMcC/KH | 2026-06-01 | 2026-09-01
E1. We recommend the Association:
6 | a) provide structured IT cybersecurity training to all staff and Board members (the use of a centralised e-learning platform may be the most efficient approach in this respect); | 2 | Platform based on-line training has been identified and booked for staff. Awaiting board approval to book training for board members. | KH | 2026-07-01 | Training has been sourced
| b) ensure that once operational, training completion rates are monitored and follow up action taken for instances where training is not completed by the communicated deadline; and | 2 | Monthly review of completed training. Follow up emails to learners, report progress/completion of training to FARC. |  |  | and staff and Members notified
| c) introduce the use of phishing simulations within the organisation with a view to enhancing staff awareness in this respect and to identify any further training needs. Third party support may be needed in this regard. | 2 | These tests will be undertaken as part of the penetration testing. | WMcC/KH | 2026-06-01 | 2026-11-04