## Sheet1
Business Plan Monitoring Summary
| Key Strategic Priority | Measures taken to achieve objective | Progress to 30/6/25
1 | Provide good quality homes | Develop Planned maintenance programme in | PMP has been developed and approved by the Board. Work
|  | consultation with each Community | has started on certain projects. At 30/6/25 we have spent
£x and completed x number of projects.
|  | Report progressof PMP at each Board meeting | This is a standing item on Board meeting agenda.
Board report attached.
|  | Develop an appropriate standard against which | This work is underway. We expect to have a first draft by
|  | the quality of our homes can be monitored. | later this year.
|  | Develop a 5 year plan for each property,starting | We aim to commence this work in August/September
with pilot of 2 properties in year ending 31/3/26
Business Plan Monitoring Summary
| Key Strategic Priority | Measures taken to achieve objective | Progress to 30/6/25
2 | Provide high quality services | Develop our maintenance service through use | We currently are using the Fusion 21 framework. We are
|  | of approproate procurement frameworks and | also considering 2 other frameworks.
further developing our Omniledger system.
|  | Monitor service by regular reporting of KPIs at | KPI.s will be provided quarterly.
each Board meeting.
|  | Complete quality assessments of work done. | Numbers assessed and results will be provided qrtly
|  | Post inspect at least 25% of response jobs. | as above
Ensure all statutory works are completed fully
and on time.
Business Plan Monitoring Summary
| Key Strategic Priority | Measures taken to achieve objective | Progress to 30/6/25
3 | Foster our partnership with | Further develop our Tenant Participation
| the Camphill Community | programme
Undertake appropriate annual tenant satisfaction
surveys, and report results and proposed actions
to Board.
Hold regular maintenance group meetings.
Hold quarterly meetings with Community
management at each community.
Hold annual " Chair to Chair" meetings.
Arrange to hold a Board meeting in at least one
of the Communities.
Review the JMAs every 2 years.
Work collaboratively with CCT to ensure that
the infrastructure on each community is fit for
purpose.
Business Plan Monitoring Summary
| Key Strategic Priority | Measures taken to achieve objective | Progress to 30/6/25
4 | Continue to build an effective | Produce annual budgets approved by the Board
and sustainable organisation
Produce qrtly Management accounts, compare
to budget, and present to Board for scrutiny.
Further develop and monitor Risk Register
Carry out annual Board effectiveness review
Undertake regular reviews of all Policies.
Update the Long Term Financial Plan annually.
Develop our website.
Further develop VfM analyses.

## Revised draft
Business Plan Monitoring Summary
Target
Key Strategic Priority 1 : Provide good quality homes | Completion | Progress to 15 August 2025
Date
Develop Planned maintenance programme in | 2025-04-01 | Plan fully developed and work underway
consultation with each Community
Report progress of PMP at each Board meeting
Develop an appropriate standard against which
the quality of our homes can be monitored.
Develop a 5 year plan for each property,starting
with pilot of 2 properties in year ending 31/3/26
Key Strategic Priority 2 : Provide high quality services
Develop our maintenance service through use
of approproate procurement frameworks and
further developing our Omniledger system.
Monitor service by regular reporting of KPIs at
each Board meeting.
Complete quality assessments of work done.
Post inspect at least 25% of response jobs.
Ensure all statutory works are completed fully
and on time.
Key Strategic Priority 3 : Foster partnership with Camphill
Further develop our Tenant Participation programme
Undertake appropriate annual tenant satisfaction surveys
Hold regular maintenance group meetings.
Hold quarterly meetings with Community management
Hold annual " Chair to Chair" meetings.
Arrange to hold a Board meeting in at least one Community
Review the JMAs every 2 years.
Work with CCT to ensure that infrastructure fit for purpose
Key Strategic Priority 4 : Build sustainable , efficient organisation
Produce annual budgets approved by the Board
Produce qrtly Management accounts, compare to budget
Further develop and monitor Risk Register
Carry out annual Board effectiveness review
Undertake regular reviews of all Policies.
Update the Long Term Financial Plan annually.
Develop our website.
Further develop VfM analyses.

## Draft 2
Business Plan Monitoring Summary
Target
Key Strategic Priority 1 : Provide good quality homes | Completion | Progress to 15 August 2025 | Appendix | Status
Measures taken to achieve objective | Date |  | Ref
Develop Planned maintenance programme in | 2025-04-01 | Plan fully developed and work underway
consultation with each Community
Report progress of PMP at each Board meeting | n/a | Qtrly reporting to Board in place
Develop an appropriate standard against which | 2026-03-04 | Work is ongoing on "own" standard
the quality of our homes can be monitored.
Develop a 5 year plan for each property,starting | 2026-03-04 | Work is underway
with pilot of 2 properties in year ending 31/3/26
Key Strategic Priority 2 : Provide high quality services
Measures taken to achieve objective
Develop our maintenance service through use | n/a | Currently in 3 frameworks: Fusion21,
of approproate procurement frameworks and |  | Frameworx, & Pagabo
further developing our Omniledger system.
Monitor service by regular reporting of KPIs at | n/a | Qtrly reporting to Board in place
each Board meeting.
Complete quality assessments of work done. | n/a | All currently up to date
Post inspect at least 25% of response jobs. | n/a | All currently up to date
Ensure all statutory works are completed fully | n/a | All currently up to date
and on time.
Business Plan Monitoring Summary
Target
Key Strategic Priority 3 : Foster partnership with Camphill | Completion | Progress to 15 August 2025 | Appendix | Status
Measures taken to achieve objective | Date |  | Ref
Further develop our Tenant Participation programme | 2025-12-03 | Tenant participation strategy to be reviewed.
Undertake appropriate annual tenant satisfaction surveys | 2025-08-31 | TSS fieldwork completed, report underway
Hold regular maintenance group meetings. | n/a | M.O. on site at least weekly
Hold quarterly meetings with Community management | n/a | Regular qrtly meetings are held
Hold annual " Chair to Chair" meetings. |  | To be arranged
Arrange to hold a Board meeting in at least one Community | 2025-08-27 | Board meeting in Mourne Grange
Review the JMAs every 2 years. | 2026-11-01
Work with CCT to ensure that infrastructure fit for purpose | n/a | Regular meetings held and reports to Board
Key Strategic Priority 4 : Build sustainable , efficient organisation
Measures taken to achieve objective
Produce annual budgets approved by the Board | 2024-04-01 | Budgets produced and approved by Board
Produce qrtly Management accounts, compare to budget | n/a | Qtrly reports prepared for Board
Further develop and monitor Risk Register | 2025-08-27 | FARC updating current RR
Carry out annual Board effectiveness review |  | Chair is currently undertaking this
Undertake regular reviews of all Policies. | 2025-08-31 | 6 policies due for review
Update the Long Term Financial Plan annually. | 2025-11-12 | Ist draft ready for FARC review
Develop our website. | n/a | Website is regularly reviewed
Further develop VfM analyses. | 2025-11-12 | To be prepared for FARC approval