## Sheet1
Risk Management - Emerging Issues Log - 14/8/26
Current
Date | Category | Nature of issue | Status
2025-06-04 | Land & Title | The registered ownership of land is unclear in some cases. An exercise is | Under review
currently being undertaken by Colin Harper,(CCT), and WMcC to determine
the land owned by CHA in Glencraig. It was planned to complete this work
by 31/3/26, but this has not been achieved.
WMcC met CH on 22 October to consider the boundaries of CHA owned
properties at Glencraig. We discussed the maps which Board Members had
reviewed on 11/6/25. There were few major points of disagreement except for
Craigowen House. CH believes that the land this house has been built on is
leased from CCT to CHA on a 50 year lease dating from 1994. There is a lease
which lists Craigowen House, but I believe this refers to the original Craigowen
House which predated the current property which was a complete rebuild
funded by HAG.
HAG requires that the recipient, (in this case CHA), must be the owner of the
land, so it is reasonable to assume that there has been a revision to this lease.
Whilst there is still 19 years remaining on the lease, this issue needs to be
clarified.
The CHA Board considered this issue at it's meeting on 17 June 2026 and
agreed that it is CHA's contention that it owns the land and if CCT has any
concerns the onus is on them to bring these forward. It was agreed to retain
the matter on the Emerging Issues log as under review.
2025-06-04 | Glencraig infrastructure | The incident in December 2024 when Glencraig lost all electricty due to an | Under review
exceptionally rare circumstance, (a rat had eaten through cables), highlighted
the need to consider what steps/ procedures could be put in place to avoid
disruption on such a large scale. A small working group had been set up to
review the current infrastructure and consider options to mitigate these risks.
Risk Management - Emerging Issues Log - 14/8/26
Current
Date | Category | Nature of issue | Status
One of the outcomes of the working group discussions was a proposal for
Glencraig to purchase appropriate standby power supply.
CHA Board agreed to proposals from the working group to make a contribution
of up to £40,000 towards the purchase of appropriate generators which would
be sufficient to ensure continuity of power supply to the Community. It was
agreed that Glencraig would procure the generators. This process is currently
underway.
2026-02-04 |  | At the latest meeting of the working group on 4 February 2026 Colin Harper of
CCT stated that his organisation had not agreed to the proposals for each
party to contribute up to £40,000. We have sought clarification on this as both
CHA and Glencraig understood that this had been agreed. The purchase of the
large generator has been halted until this is resolved.
2026-05-22 |  | Colin Harper of CCT has stated that they are not prepared to contribute towards
the cost of 2 mobile generators which were included in the original agreement
at an estimated £5,000 each.He has also requested that 2 new specifications
are drawn up by different consultants. One of these will then be selected to
prepare the tender documentation.
The effect of this is to stall the whole project and it may be several months before
there is any further progress. It is also worth noting that the change of CEO at
Glencraig, with Paul Betts retirement will most likely delay the project.
2026-06-10 |  | The Planning committee considered this issue at its meeting on 10 June 2025
and agreed to consider further action including proposing the purchase of 2
mobile generators by CHA if there has not been any substantial movement
in the original project by mid July.
This issue remains under review.
Risk Management - Emerging Issues Log - 14/8/26
Current
Date | Category | Nature of issue | Status
2026-08-03 | Glencraig infrastructure | I contacted CH and asked him to reconsider his decision not to include the | Under review
mobile generators in the overall amount for the project. He stated he would
now include these, and I asked him to email me confirmation which he did.
It now appears the project is back on track.
2025-11-12 | Breakdown in relations between Board and Co-workers in Clanabogan
|  | There is a long running dispute between the Board and Co -workers which has | Under review
escalated to the point of legal proceedings being taken. I am not aware of
the detail of this dispute. At present there has been no disruption to the care
of residents or any other operational issues.
FARC considered that this issue should be included in the log and kept under
regular review.
In January a new Manager, Una Davey was appointed in Clanabogan. I met
Una in January, she is an experienced manager and appears to have settled
in very quickly.
2026-05-14 |  | Chris Thompson & WMC met Una Davey,( the recently appointed Manager at
Clanabogan), Diane Stevenson (Chair of Clanabogan Board), and Neville
Armstrong, (Board Member). This was an open and constructive meeting which
provided reassurance that the Board are working diligently in the best interests
of residents. A brief note of the meeting will be presented to Members at the
Board meeting on 17th June.
This issue will be kept under review.
Risk Management - Emerging Issues Log - 14/8/26
Current
Date | Category | Nature of issue | Status
2026-07-31 | Kim Harper left for new job | Issue is that it has proven difficult to get a suitable replacement quickly. The | Under review
Staffing and Remuneration Cttee have met and are involved in the recruitment
process.
This issue will be kept under review, to ensure it does not escalate to become
| . | a risk.