## Summary
Planned Maintenance Programme 2025 to 2026
Summary of PMP completed against budget
2025-08-22 | [6 empty] | Association
|  | Glencraig |  | Mourne Grange |  | Clanabogan | Totals
£
PMP Budget for year |  | 92950 |  | 140520 |  | 70460 | 303930
Cost of Work completed YTD | 2A | 25420 | 2B | 0 | 2C | 24784 | 50204
Work currently underway | 3 | 0 | 3 | 0 | 3 | 0 | 0
Estimated £ committed to date |  | 25420 |  | 0 |  | 24784 | 50204
£ of over or - under spend to date |  | -67530 |  | -140520 |  | -45676 | -253726
% of budget committed |  | 27.35% |  | 0% |  | 35.17% | 16.52%

## Sch 2
Glencraig - Draft PMP 2025 - 2026 |  |  |  | Sch 2A
|  | Estimated | Completed
Property | Project | Cost | Actual cost
|  | £ | £
Pestalozzi | Replace stairs & FF floor carpets | 2000 | 0
| Refurb FF bathroom | 6000 | 0
|  | 8000 | 0
Hermitage | External redecoration | 3500 | 4250
| Replace lounge flooring | 500 | 0
|  | 4000 | 4250
Samaria | Replace carpet on stairs & landing | 1000 | 1015
|  | 1000 | 1015
Lodge | Replace kitchen | 9000 | 0
|  | 9000 | 0
Kintyre | Replace G/F cork flooring to vinyl | 3500 | 0
| Renew kitchen doors | 1500 | 0
|  | 5000 | 0
Del O Grace | Replace laundry flat roof | 3000 | 0
|  | 3000 | 0
Craigowen House | Refurb bathroom 209 | 7000 | 0
| Internal redecoration, incl.doors | 10000 | 8901
|  | 17000 | 8901
Bethany | Upgrade Front door to PVC | 2000 | 0
| Refurb bathroom (202 or 207) | 8000 | 0
| External redecoration | 6000 | 4450
|  | 16000 | 4450
Emmaus | Renew carpets to vinyl on landing / stairs | 4000 | 0
| Redecorate FF hall | 1000 | 2802
|  | 5000 | 2802
Novalis | Sand and seal dining room floor | 500 | 0
| Refurb bathroom | 7000 | 0
|  | 7500 | 0
Comgall | Internal redecoration | 7500 | 4002
| Replace FF carpets with vinyl | 1500 | 0
|  | 9000 | 4002
| Total projects by property | 84500 | 25420
| Contingency | 8450
|  | 92950 | 25420
Mourne Grange
Draft Planned maintenance programme |  |  |  | Sch 2B
|  | Estimated | Completed
Property | Project | Cost | Actual cost
|  | £ | £
Avalon | Replace ext door to boot room | 1000 | 0
|  | 1000 | 0
Coach | Refurb downstairs bathroom | 4000 | 0
| Replace 2 ext store doors | 600 | 0
|  | 4600 | 0
Arimathea | Overhaul roof along-with Nicodemus | 2500 | 0
|  | 0 | 0
|  | 2500 | 0
Iona | Replace front door set | 2000 | 0
| Refurbish kitchen(resand/spray doors) | 3000 | 0
| Refurb GF bathroom | 5000 | 0
|  | 10000 | 0
Nicodemus | Overhaul roof along-with Arimathea | 2500 | 0
| Renew main entrance door set | 2000 | 0
|  | 4500 | 0
Skellig Michael | Internal redecoration | 4000 | 0
| Refurb bathroom(209) | 5000 | 0
|  | 9000 | 0
St Bronagh | Refurb bathroom(111) | 5000 | 0
|  | 0 | 0
|  | 5000 | 0
Raphael | Refurb WC(116) & bathroom(117) | 8000 | 0
| Replace flooring in entrance & hallways | 3000 | 0
|  | 11000 | 0
MG House | External redecoration | 6000 | 0
| Renew extractor fans | 1000 | 0
|  | 7000 | 0
St Sunniva | Refurb 2 bathrooms | 10000 | 0
|  | 10000 | 0
Tobias | Upgrade whole property | 36000 | 0
|  | 36000 | 0
Fairy Grove | Refurb bathroom 103 | 3000 | 0
|  | 3000 | 0
Shimna Lodge | Replace rear ext door | 1500 | 0
| Refurb 2 bathrooms | 12000 | 0
|  | 13500 | 0
| Total projects by property | 117100 | 0
| Add: Contingency | 11710
| Add: In year projects | 11710
|  | 140520 | 0
Clanabogan
Draft PMP for year ending 31/3/26 |  |  |  | Sch 2C
|  | Actual | Completed
Property | Actionable | Cost | Actual cost
|  | £ | £
Artaban | Internal redecoration | 2800 | 2800
| Replace flooring in bedrooms corridor | 2000 | 2064
| Replace windows at rear | 12500 | 0
|  | 17300 | 4864
Columba
|  | 0 | 0
Rainbow | Internal redecoration | 2400 | 2400
| Replace upstairs carpet with laminate | 2000 | 0
| Refurb upstairs bathroom(113) | 7500 | 7560
|  | 11900 | 9960
Riverstown | Internal redecoration | 3600 | 3600
| Replace suspended ceiling | 2000 | 3960
|  | 5600 | 7560
Sloe | Renew kitchen | 9500 | 0
|  | 9500 | 0
Sunrise | Internal redecoration | 2400 | 2400
| Refurb upstairs bathroom | 7500 | 0
|  | 9900 | 2400
| Total projects by property | 54200 | 24784
| In year projects | 5420
| Add: Contingency | 10840
| Total proposed | 70460 | 24784

## Sch 3
Sch 3
Glencraig
|  | Estimated | Completed
Property | Project | Cost | Actual cost
|  | £ | £
Samaria
Emmaus
Comgall
0
Mourne Grange
|  | Estimated | Completed
Property | Project | Cost | Actual cost
|  | £ | £
0
Clanabogan
|  | Estimated | Completed
Property | Project | Cost | Actual cost
|  | £ | £
0