## Outstanding Items
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2024-10-23 | Website development SL was asked to contact GMcC who had agreed to assist in the presentation of photos on the site.WMcC was asked to circulate the link to the draft website to Members. It was also agreed that WMcC would follow up on the use of a drone to capture aerial images of the Communities. | SL/WMcC | SL discussed with GMcC and the website is now live. We plan to have drone photos taken in the summer. |  | Target 31/10/25
2 | 2024-12-18 | Glencraig power outage This incident where a rat had eaten through electric cables inside a mini sub-station causing a widespread power outage , highlighted the need for a greater understanding between CHA, CCT and Glencraig regarding their respective responsibilities for the infrastructure in the Community. To consider these issues, a working group comprised of staff from Glencraig, CCT, & CHA was created. | WMcC | The primary focus of the working group has been on agreeing measures to mitigate the risk of future power failure at the Community. The group has agreed that this can only be achieved by the purchase of appropriate diesel generators. Paper 2B sets out a brief proposal on the contribution required from CHA. |  | 2026-03-31
3 | 2025-04-23 | Board refreshment AH suggested that the Board should consider future replacements for both RB and himself. He asked WMcC to contact all Board Members to evaluate Board competencies and identify skill gaps that could be filled with targeted recruitment of future Members. | AH | Questionnaires were sent out to Members and the results have been collated at Paper 2A | Y | Target 27/08/25
4 | 2025-04-23 | Qualitative review of response maintenance AH asked that Stephen and Michael undertake a qualitative review of response maintenance jobs for Board evaluation. | SL/MC | Work is underway on this project and a report will be presented to the Board when this is complete. |  | Target 31/10/25
5 | 2025-06-18 | Amendments to Risk Management Policy & Risk Management Strategy At the Board meeting on 18 June 2025, Members agreed to review the changes proposed by FARC to the Risk Mgt Policy & Risk Mgt Strategy before the next Board meeting scheduled for 27 August. | SC | These documents were sent to Members on 23 June for review.Issues arising are scheduled for consideration at agenda item 5. |  | Target 31/10/25
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
6 | 2025-06-18 | Land & Title The FARC was asked to consider whether the issues relating to boundaries and land ownership should be included in the Risk Regsister | FARC | FARC considered this and agreed that this issue should remain on the Emerging issues log rather that being escalated to the Risk Register. | Y | Target 31/10/25
7 | 2025-06-18 | Timing of the AGM AH proposed moving the date of the AGM from June to September to allow more time for preparations of Accounts, Annual Report, etc. | WMcC | WMcC explained that the current Association rules state that the AGM must be held within 3 months of the year end. WMcC was asked to research changing the rules to accommodate moving the date of the AGM. I have received a copy of the new model rules produced by NIFHA. For the next BM I will prepare a paper showing changes from our current rules and the process to be followed to change. |  | Target 3/12/25