## Outstanding Items
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2022-10-26 | Energy Efficiency Survey WMcC proposed sharing the Expression Of Interest, when agreed by the Board, to appropriate consultants on Fusion 21’s call off list. | WMcC | The original action point envisaged appointing external Consultants to undertake a comprehensive survey of all properties with the expectation of this being at least partly funded by DfC. This is clearly not going to happen and, if Members are content, I propose that this action point is closed. The Board approved a budget of £18,000 to spend on energy efficiency measures at Clanabogan, and work is underway on this. Board updates will be provided in the maintenance report. | Y | 2024-08-16
2 | 2021-02-10 | Tenancy Agreements The Board consider that Tenancy Agreements should be in place for Glencraig. | WMcC | The revised JMA has now been agreed and signed by both parties. This includes an Occupancy Agreement for Resident Co-Workers and Stepped back Co-Workers. | Y | 2024-08-06
3 | 2023-08-23 | GDPR Refresher training WMcC was asked to source traing for both Members and staff on GDPR. | WMcC | The Information Commissioners Office have stated that they are considering organising an information session with NIFHA and will update us in due course. No dates have been confirmed yet. | ongoing | Target Early 2025
4 | 2023-12-13 | Board refreshment It was noted that efforts should be continued to secure Tenant representation from Clanabogan and Mourne Grange if possible. | LD | LD has raised this issue at Camphill Northern Neighbourhood meetings and will continue to explore options. | ongoing | Target 31/12/24
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
5 | 2023-12-13 | St Sunniva septic tank The flooding in December raised concerns around the operation of the septic tank. | MC | The septic tank is old and showing signs of damage. There is also evidence that the soak-away is not operating as it should be, an issue which was exacerbated by the heavy rain. Following site visits with Consultant from Precision Group, proposal is to install a new septic tank in a more appropriate location which will facilitate proper soakaway. The replacement of the septic tank is budgetted for in the PMP. We are finalising costs and expect work to be completed before the end of the year. | Y | Target 31/12/24
6 | 2024-02-21 | Internal Audit Review The Risk management review undertaken by ASM recommended that Board and staff receive training on risk management. | WMcC | Sumer(NI), formerly ASM), agreed that training could be provided in October, but no firm dates have been proposed yet. | ongoing | Target 31/10/24
7 | 2024-04-24 | Glencraig occupancy WMcC to follow up on obtaining the occupancy numbers for Glencraig. | WMcC | We have received the numbers of residents,co-workers and co-workers children, but not names. I propose to raise this formally with Paul Betts, CEO of Glencraig , at our next quarterly meeting scheduled for 28 August. . | ongoing | Target 30/9/24
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
8 | 2024-06-26 | Policy reviews Several Policies were due to be reviewed in line with RSAR requirements. | WMcC | The Policies have been reviewed and Members amendments have been included. Board Members approved the reviews. | Y | 2024-08-16
9 | 2024-06-26 | Corporate Calendar RB asked that the Corporate Calendar Summary is presented to the Board at each meeting. | WMcC | Corporate Calendar Summary is attached at appendix 2A. | Y | 2024-08-16
10 | 2024-06-26 | Amendment to Financial Reporting Standard FRS 102 SC advised that a change to FRS 102 may have an impact on the Association. WMcC was asked to clarify the issue with the external Auditors. | WMcC | I contacted GMcG and they confirmed that the changes which do not come into force until 2026 will not have any impact on CHA. I have attached copy of response from GMcG at appendix 2B | Y | Target 31/10/24