## Sheet1
Risk Management - Emerging Issues Log - 7/8/2025
Current
Date | Category | Nature of issue | Status
2025-04-23 | Board refreshment | AH and RB are approaching the final years of their Board tenure. | Under review
Members need to ensure that planning for replacements is considered
at an early stage.
There are currently 2 potential candidates interested in Board membership.
2025-06-04 | Land & Title | The registered ownership of land is unclear in some cases. An exercise is | Under review
currently being undertaken by Colin Harper,(CCT), and WMcC to determine
the land owned by CHA in Glencraig. It is planned to complete this work
by 31/3/26.
WMcC will provide updates at each Board meeting.
2025-06-04 | Glencraig infrastructure | The incident in December 2024 when Glencraig lost all electricty due to an | Under review
exceptionally rare circumstance, (a rat had eaten through cables), highlighted
the need to consider what steps/ procedures could be put in place to avoid
disruption on such a large scale. A small working group has been set up to
review the current infrastructure and consider options to mitigate these risks.
WMcC will provide updates at each Board meeting.