## Outstanding Items
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2023-08-23 | GDPR Refresher training WMcC was asked to source training for both Members and staff on GDPR. | WMcC | I have contacted the Information Commissioner's Office, NICVA and NIFHA, and all stated that they have no immediate plans to provide any further training on GDPR. The ICO directed me to the information available on their website, which appears to be fairly comprehensive. This can be accessed at ico.org.uk. | ongoing | Target Early 2025
2 | 2023-12-13 | Board refreshment It was noted that efforts should be continued to secure Tenant representation from Clanabogan and also seek finance/accountancy experience. | LD | LD has raised this issue at Camphill Northern Neighbourhood meetings and other avenues are also being actively followed up. | ongoing | Target 31/12/24
3 | 2024-02-21 | Internal Audit Review The Risk management review undertaken by ASM recommended that Board and staff receive training on risk management. | WMcC | Sumer(NI), formerly ASM), have proposed a training session for 6/11/24. Brief paper is attached at 2B | Y | 2024-11-06
4 | 2024-04-24 | Glencraig occupancy WMcC to follow up on obtaining the occupancy numbers for Glencraig. | WMcC | We have received the numbers of residents,co-workers and co-workers children, but as yet not names. However, Glencraig staff have confirmed that this information will be provided quarterly from 31/10/24. | ongoing | Target 31/10/24
5 | 2024-08-21 | RSAR 2023 TO 2024 WMcC to circulate the draft RSAR documentation to Members for their review, comments and approval by 23 September. | WMcC | Members comments were taken into account and final RSAR submitted on 3rd October. | y | 2024-10-03