## Outstanding Items
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2024-10-23 | Decent Homes Standard WMcC was asked to keep Board Members updated on DfC review of the Decent Homes Standard and of relevant developments in England. | WMcC | At the Board meeting on 18th December, it was agreed that the Association would develop an appropriate standard for it's properties. This action is included in the Business Plan and will now be monitored by the Planning Cttee. | Y | Target 31/3/26
2 | 2024-10-23 | Website development SL was asked to contact GMcC who had agreed to assist in the presentation of photos on the site.WMcC was asked to circulate the link to the draft website to Members. It was also agreed that WMcC would follow up on the use of a drone to capture aerial images of the Communities. | SL/WMcC | SL discussed with GMcC and the website is now live. We plan to have drone photos taken in the summer. |  | Target 31/10/25
3 | 2024-12-18 | Board meeting venue WMcC was asked to enquire whether a Board meeting could be held at a Camphill Community. | WMcC | Arrangements have been made to hold the Board meeting scheduled for 27 August at Mourne Grange. This will include meeting residents and visits to houses and workshops. | Y | 2025-08-27
4 | 2024-12-18 | Glencraig power outage This incident where a rat had eaten through electric cables inside a mini sub-station causing a widespread power outage , highlighted the need for a greater understanding between CHA, CCT and Glencraig regarding their respective responsibilities for the infrastructure in the Community. Paul Betts has arranged three meetings to date between Colin Harper of CCT and WMcC to consider these issues. | WMcC | There have been no further meetings between CHA, CCT and Glencraig since the last Board meeting, as further exploratory surveys are being undertaken by electrical Contractors. It is expected that these contractors will report towards the end of June. A meeting has been scheduled for 2 July. |  | 2026-03-31
5 | 2025-04-23 | Board refreshment AH suggested that the Board should consider future replacements for both RB and himself. He asked WMcC to contact all Board Members to evaluate Board competencies and identify skill gaps that could be filled with targeted recruitment of future Members. | WMcC | Quetionnaires were sent out to Members and the results have been collated at Paper 2B |  | Target 27/08/25
6 | 2025-04-23 | Qualitative review of response maintenance AH asked that Stephen and Michael undertake a qualitative review of response maintenance jobs for Board evaluation. | SL/MC | Work is underway on this project and a report will be presented to the Board when this is complete. |  | Target 31/10/25
7 | 2025-04-23 | Internal Audit plan Members considered various options for the 2025-2026 Internal Audit plan, including Financial management, Procurement, and Value for Money. It was agreed that FARC will consider this and bring proposals to the next Board meeting. | FARC | FARC considered this and after consulting SUMER agreed to propose that the IA programme for 2025 to 2026 is to have 2 assurance reviews, starting with IT security and following this with a review of VfM which will include procurement. | y | Target 31/7/25