Proposed amendments to risk register

CR2 – Amend Target completion date from 31/7/25 to 30/9/25.

CR2 -  At Board meeting on 18 June the Board amended the residual risk from green              to amber due to the risk posed by injury or damage caused by falling trees. We have tree surveys completed at each Community and are currently following up quotations for remedial works required.