## All action points
FARC Meetings - Summary of Action Points PAPER 2
Completed Actions marked in green
Date of FARC Meeting | Action Point | Responsible | Comments | Completed | Date
2019-06-19 | Treasury Policy RB to liaise with WMcC to amend policy in line with cttee discussions. | RB/WMcC |  | Y | 2019-07-01
2019-06-19 | Review of Risk Register CR3 Add risk of Clanmil withdrawing maintenance service CR4 Delete action planned to visit other HAs in GB & Ireland CR5 Approval of RSAR is not responsibility of FARC, this should be approved by Board. WMcC to schedule Special Board Meeting for this purpose. | WMcC |  | Y | 2019-06-01
2019-06-19 | WMcC to raise the issue of amending the wording of notes 19 and 21 in Financial Statements with the Auditors as outlined by FARC members. | WMcC |  | Y | 2019-06-01
2019-06-19 | RB asked WMcC to convey to the external auditors the Committee’s disappointment at the delay in the accounts. | WMcC |  | Y | 2019-06-01
2019-03-27 | Rent setting AH asked WMC to look again at the inflation rate as close as possible to the time of the rent setting process to provide evidence to back up any requested housing benefit increase and suggested that talking to other housing associations could also be helpful. | WMcC | This will be reviewed in August/Sept for increases to be applied in October
2019-03-27 | Planned Maintenance Programme For the next Board meeting, a paragraph is to be added to the Board papers to explain the approval process for 1) items included in the SCS and 2) those items not included in the SCS requiring further explanation and a business case. A narrative explaining what the requested £780k will deliver for CHA and the Communities is also required. | WMcC |  | Y | 2019-04-01
2019-03-27 | Planned Maintenance Programme Projects identified outside of the SCS must ultimately be supported by a business case. WMcC to add an additional column headed “subject to business case” to the planned maintenance schedule to separately identify these items. | WMcC |  | Y | 2019-04-01
2019-03-27 | Budgets for year ending 31 March 2020 The budget for bank interest should be allocated equally across the three Communities | WMcC |  | Y | 2019-04-01
2019-03-27 | Budgets - HMO Charge In the past there have been no registrations for Glencraig, the assumption being that Glencraig has made their own applications or possibly registrations are not required due to the nature of their funding. This will be investigated further. | WMcC | Belfast City Council has confirmed that Housing Association properties fall outside the definition of HMOs and registration is therefore not required. | y | 2019-04-01
2019-03-27 | Budgets for year ending 31 March 2020 The term “service charges” stated in the budget paper is confusing and should be amended to read “contribution to Maintenance Officers” and a note added to the budget schedule stating that the contribution had been previously approved by the Board as part of the rent setting process. | WMcC |  | Y | 2019-04-01
2019-03-27 | Internal Audit – Financial Management review Three low level recommendations have been made in the appendices of the Financial Management Review report | WMcC |  | Y | 2019-05-01
2019-03-27 | Risk Register RB proposed the inclusion of an additional risk to incorporate the actions to be taken under the Way Forward Committee recommendations. The risk should read “lack of strategic leadership in developing the way forward for the organisation” and the columns should be coloured red and amber respectively. | WMcC |  | y | 2019-04-01
2019-03-27 | CR5 – failure to achieve necessary standards of governance Under controls in place the following should be added: • Annual review of rents • Planned programme of review of policies | WMcC |  | y | 2019-04-01
2019-03-27 | Risk Register CH suggested that the risk register is amended to include a reference specifically to the RSAR | WMcC |  | Y | 2019-04-01
2019-03-27 | Check when RSAR papers will be released | KB | WMcC checked with Jacky Richardson. Papers will be released at the end of May. | Y | 2019-04-01
2019-03-27 | CR5 – failure to achieve necessary standards of governance The Committee agreed to set the risk to red because of the potential unfavourable scoring from the RSAR. This will be reviewed in June and, amended to amber if a score of 3 is achieved. The second column should be coloured amber. | WMcC |  | Y | 2019-04-01
2019-03-27 | CR6 - lack of resources Because the staffing issue has been resolved with the engagement of a Maintenance Officer, this risk should now be set to green. | WMcC |  | Y | 2019-04-01
2019-03-27 | CR1 - failure to achieve the required rental income The “control in place” relating to financial support to the Communities from CCT NI. should be removed as this financial support is not CHA’s control. | WMcC |  | Y | 2019-04-01
2019-03-27 | Risk Register CR1 risk should be reduced to 2 | WMcC |  | Y | 2019-04-01
2019-03-27 | Risk Register Action Plan WMcC agreed to amend the target date for the completion of the first annual report to the CCNI to September. Information to support the completion of the report will be available from June so there is no requirement to wait until January 2020. | WMcC |  | Y | 2019-05-01
2019-03-27 | Performance appraisals for staff will be carried out during April. | WMcC/Staff |  | Y | 2019-05-01
2019-03-27 | WMcC’s performance review to be completed by the end of April. | AH/WMcC |  | Y | 2019-07-25
2019-03-27 | Board Membership - RSAR query Prepare a draft of how the DfC query on Board membership/refresh will be addressed for presentation at the next Board meeting in April | WMcC |  | Y | 2019-04-01
2019-03-27 | He asked KB to contact JN and CM to confirm their intention to leave and to get an indication of the timings. | KB | Both CM and JN advised that they would resign after the AGM in June | Y | 2019-04-01
2019-03-27 | CH offered to supply an example of a Business Continuity Plan to facilitate the drafting process. RB requested that the need for a location specific BCP is considered in light of the model BCP provided by ASM. | CH | CH advised at the June FARC that an example was currently being prepared and would be supplied in due course |  | on going
2018-11-07 | The DfC asked for an outline of the succession planning and arrangements that the association has in place pertaining to Board member renewal and recruitment. A response is due by Friday 9th November 2018 – WMcC will arrange to reply accordingly. | WMcC |  | Y | 2018-11-01
2018-11-07 | WMcC to prepare a letter of authorisation for the bank and draft a paper concerning on-line banking for presentation to the Board. | WMcC | WMcC/KB met Bank official to prepare for proposals to present to Board | Y | 2019-06-01
2018-11-07 | It was agreed that GDPR should be listed on the Risk Register as a separate item. | WMcC |  | Y | 2019-01-01
2018-11-07 | Review of risk register WMcC to place Resourcing on the Risk Register. | WMcC |  | Y | 2019-01-01
2018-11-07 | Review of risk register WMcC was asked to check the CCNI registration and confirm that all details are correct including existing members. | WMcC |  | Y | 2018-11-01
2018-11-07 | Review of risk register - JMAs Action plan dates (relating to JMAs) need to be moved to 31/03/19. A comment is to be included to reflect that the completion date is dependent on the cooperation of the communities. | WMcC |  | Y | 2018-11-01
2018-11-07 | JMA Regarding Glencraig no further progress has been made re the JMA. AH advised he believed there were some guidance notes contained on the Charity Commissioners website regarding the responsibilities of the Trustees. He advised he would try to source this information | AH |  | Y | 2019-03-01
2018-11-07 | Internal Audit Tender WMcC to proceed to with tender for Internal Audit. | WMcC | Tender process completed, ASM appointed. | Y | 2018-12-01
2018-08-06 | Internal Audit Update - Financial Management WMcC advised that the documentation of payroll procedures and controls will be completed in August. Karen Breddy will run the payroll and WMcC will review and sign off. Salary cheques continue to be signed by two Board members. | WMcC/KB | Segregation of duties is difficult with only 2 members of staff trained to run payroll - Holiday cover remains an issue | Y | 2018-09-01
2018-08-06 | Internal Audit Update – Financial Management Policies relating to financial management have been scheduled for completion in August and September. | WMcC |  | Y | 2018-09-01
2018-08-06 | Internal Audit Update – Financial Management WMcC agreed to look at Bankline, or a similar electronic banking system. | WMcC |  | Y | 2019-06-01
2018-08-06 | GDPR - Data Retention JC confirmed that information on data retention has been prepared and must go to the Board for approval. | JC | A data retention document was included in the May board meeting papers | y | 2018-08-29
2018-08-06 | GDPR - Data Requests There is a requirement to identify what data is held by CHA and where/how this data is held. JC confirmed that a data inventory is yet to be prepared. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01
2018-08-06 | GDPR The main priority is registration with the ICO. An action plan will follow once this has been completed to cover remaining steps. The registration process can proceed once the registration statement has been approved by the Board. | WMcC/KB |  | Y | 2019-02-01
2018-08-06 | GDPR RB requested a table for the next Board meeting summarising where CHA is at the moment, what is still to be done and who is responsible. | JC |  | Y | 2018-08-01
2018-08-06 | AH requested that a summary of action points is prepared following each Committee meeting and completion dates/comments recorded. | KB |  | Y | 2019-03-01
2018-08-06 | Review of the Risk Register and Action Plan CR1 (failure to achieve the required rental income in the short and longer terms) The Committee agreed that, although it appears that things are moving in a positive direction, there is still a long way to go and CR1 should remain highlighted in red. | WMcC |  | Y | 2018-08-01
2018-08-06 | Review of the Risk Register and Action Plan The Committee agreed that all actions included in the action plan should have a status indicator. | WMcC |  | Y | 2018-08-01
2018-08-06 | Review of the Risk Register and Action Plan RB referred to the requirement for a procurement policy against risk CR4. WMcC agreed to draft the policy. | WMcC | Policy has been prepared and will be presented to FARC in June | Y | 2019-06-01
2018-08-06 | Review of the Risk Register and Action Plan FARC meets approximately once every three months. RB advised that, because FARC issues are so important, the Risk Register should be reviewed on a more regular basis and requested a monthly update for presentation and review at Board meetings. | WMcC | The RR is reviewed regularly and an updated copy is made available at each Board Meeting | Y | 2019-03-27
2018-08-06 | Review of the Risk Register and Action Plan JN raised concerns over the lack of a business continuity plan. This subject is covered in the action plan under CR4 (failure to achieve appropriate standards of operational control) with a target completion date of 30/9/18. JC advised that he has already instigated discussions with the Communities on this subject. He stated that the drafting of business continuity plans is extremely complex because of the Camphill/CHA inter-relationship and shared facilities at the Camphill sites. There is a lot of investigative work involved and the co-operation of the Communities is essential. | WMcC/KB/BS |  |  | on going
2018-08-06 | Review of the Risk Register and Action Plan RB reiterated that preparation of a work plan is essential and must be included in the agenda for the August Board meeting. | WMcC/KB/JC |  | Y | 2018-08-01
2018-08-06 | Rent setting / JMA process The next stage in the JMA/rent setting process will be the rent increase submission to the Housing Executive. | WMcC |  | Y | 2018-09-01
2018-08-06 | Rent setting / JMA process The 9% rent increase must be agreed with the two Communities involved. It was suggested that WMcC explain the situation to Clanabogan management and ask for a letter, similar to the one received from Mourne Grange, to support the application to the Housing Executive. Should the Housing Executive approve a rent increase of less than 9% then the rent increases imposed on the Communities will be revisited and renegotiated. This plan of action will be proposed to the Board for approval. | WMcC |  | Y | 2018-08-01
2018-08-06 | Rent setting / JMA process The Committee agreed that assurance from CHA’s solicitors would make discussions and agreement of the JMAs shorter and simpler. WMcC will discuss this proposal with Nigel Carson and, if he agrees, send the JMA for Mourne Grange for legal review. | WMcC |  | Y | 2019-03-27
2018-08-06 | Budget revision WMcC agreed to follow up on land and title with Colin Harper and seek clarification on why Glencraig has not been finalised. | WMcC | WMcC followed up with CCT NI. They advised that they were awaiting information on other Communities. This information however had not been requested during the meeting regarding Glencraig. | Y | 2019-03-27
2018-08-06 | BC advised that the internal audit contract is now coming to an end. This issue will be followed up by WMcC. | WMcC | ASM appointed | Y | 2018-01-01
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan GDPR Project Plan - A timebound project plan is required to set out how the organisation intends to achieve compliance. | WMcC/KB | Plan will be developed with assistance from ASM. A review of progress was carried out on 12th September and ASM are currently reviewing documentation provided, actions completed and actions outstanding. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Policies and Procedures – CH reported that she had reviewed CHA’s draft GDPR policy with JC and advised changes required to make the policy compliant prior to submission to the Board for approval. | JC |  | Y | 2019-03-27
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Registration with the ICO – registration of CHA as a data processor with the ICO is required. JC reported this process is underway and he is currently working on the preparation of an ICO registration statement. | JC |  | Y | 2018-02-01
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Responding to data requests There is a need to prepare a data inventory to identify what information is held by CHA and how/where this data is held. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Data retention The Committee agreed that there is a requirement to look at what CHA needs to hold to conduct business. Any information over and above this should be destroyed. The starting point of this process will be a data inventory. JC advised that he has prepared documents on data retention and data mapping for review and approval by the Board. | JC/Board | A data retention document was included in the May board meeting papers | Y | 2018-05-01
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan WMcC should attend a GDPR training session and the DPO should receive a more structured higher level training to cover case law etc. | WMcC/KB | WMcC attended a GDPR awareness workshop in June 2019. Training material has been sent to ASM for review Sept 19. The need for further training is to be clarified. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan CH recommended that it would be prudent to seek legal advice in relation to GDPR requirements on tenancy agreements and JMAs. | WMcC/KB | New tenancy agreements for MG and Clanabogan have been drafted,agreed with CH and forwarded to Communities for signing. Glencraig tenancy arrangements/GDPR to be discussed with Paul Betts
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan RB requested that a project plan is prepared for the next Board meeting detailing actions to be taken with timescales to assure the Board that outstanding issues are being addressed. Draft policies should also be brought to the Board for review. | JC | A project plan and draft policies were included in the May board meeting papers | Y | 2018-05-01
2018-04-30 | External Audit Tender update WMcC reported that, subject to Board approval, GMcG has been selected as external auditor. Letters will be sent to all parties concerned following the Special General Meeting to be held on Wednesday 9th May. | WMcC |  | Y | 2018-05-01
2018-04-30 | Review of the Risk Register and Action Plan - (CR1) the review of the JMAs and rent setting RB suggested bringing in another resource to take forward the JMAs. It was agreed that this issue should be added to the agenda for the Board meeting. | WMcC | B Gamble appointed November 2018 | Y | 2018-05-01
2018-04-30 | Review of the Risk Register and Action Plan The planned visit to Sturts Farm will be the responsibility of the Way Forward Committee going forward and should be removed from the action plan. | WMcC |  | Y | 2019-03-27
2018-04-30 | Review of the Risk Register and Action Plan The first item on the action plan relates to on-going KPI reporting and should be set to green in line with CR2 on the risk register. | WMcC |  | Y | 2019-03-27
2018-04-30 | Review of the Risk Register and Action Plan The Risk Register will be copied to the Board for the next meeting | WMcC |  | Y | 2019-03-27
2018-04-30 | SCS/Rent setting process RB requested that WMcC prepares a report on the SCS and on rent setting forecasts for presentation to the Board at the May meeting | WMcC |  | Y | 2019-03-27
2018-04-30 | Service Charges: communication from Mourne Grange The Committee agreed that any formal response to the letter should be put on hold and that WMcC should speak to Lizzie Dixon to advise her of the following: - on the first issue relating to service charges, CHA is exploring options for resolution and will discuss in due course - on the second issue, the closure of Aurora, CHA is concerned over the view of the regulator and the impact on CHA | WMcC |  | Y | 2019-03-27
2018-04-30 | Financial Report Year end accounts will be completed in May and will be available for the June Board meeting. The AGM will take place around 28th June. | WMcC |  | Y | 2019-03-27
2018-04-30 | Financial Report WMcC presented the current draft of the 2018/2019 budget for information. An updated version will be prepared for the next Board meeting. | WMcC |  | Y | 2019-03-27
2019-06-19 | Treasury Policy RB to liaise with WMcC to amend policy in line with cttee discussions. | RB/WMcC |  | Y | 2019-07-01
2019-06-19 | Review of Risk Register CR3 Add risk of Clanmil withdrawing maintenance service CR4 Delete action planned to visit other HAs in GB & Ireland CR5 Approval of RSAR is not responsibility of FARC, this should be approved by Board. WMcC to discuss with Chair possibly holding a Special Board Meeting for this purpose. | WMcC |  | Y | 2019-06-01
2019-06-19 | WMcC to raise the issue of amending the wording of notes 19 and 21 in Financial Statements with the Auditors as outlined by FARC members. | WMcC |  | Y | 2019-06-01
2019-06-19 | RB asked WMcC to convey to the external auditors the Committee’s disappointment at the delay in the accounts. | WMcC |  | Y | 2019-06-01
2019-03-27 | WMcC’s performance review to be completed by the end of April. | AH/WMcC |  | Y | 2019-07-25
2018-11-07 | WMcC to prepare a letter of authorisation for the bank and draft a paper concerning on-line banking for presentation to the Board. | WMcC | WMcC/KB met Bank official to prepare for proposals to present to Board | Y | 2019-06-01
2018-08-06 | Internal Audit Update – Financial Management WMcC agreed to look at Bankline, or a similar electronic banking system. | WMcC |  | Y | 2019-06-01
2018-08-06 | GDPR - Data Requests There is a requirement to identify what data is held by CHA and where/how this data is held. JC confirmed that a data inventory is yet to be prepared. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01
2018-08-06 | Review of the Risk Register and Action Plan RB referred to the requirement for a procurement policy against risk CR4. WMcC agreed to draft the policy. | WMcC | Policy has been prepared and will be presented to FARC in June | Y | 2019-06-01
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Responding to data requests There is a need to prepare a data inventory to identify what information is held by CHA and how/where this data is held. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01
2020-05-11 | COVID-19 It was agreed that the Risk Register should be amended to add Covid -19 as a separate risk and WMcC was instructed to amend accordingly. | WMcC | New risk added to Register for consideration/monitoring by Cttee | Y | June
2020-05-11 | Audit Review – External Audit WMcC stated that he had held several conversations with the auditors when they explained their audit approach, but had not received any formal audit planning documentation from them.PF stated that he felt the Association should receive a more formal audit planning document which would set out in greater detail how the audit will be conducted remotely.WMcC was instructed to address this issue with the auditors. | WMcC | WMcC contacted GMcG and received Summary Audit Planning Memorandum, which has been distributed to members. | Y | May
2020-02-11 | Financial report PF advised that the current layout of the balance sheet is incorrect and advised a new layout. The report will be amended going forward to show Net Current Assets (current assets less current liabilities) and Total Assets less Current Liabilities. The available cash balance going forward will be shown on the bank balances report and will reflect the net current assets figure from the balance sheet. | KB | Reports have been amended accordingly | Y | Feb
2020-02-11 | Internal Audit Programme 2020/2021 The Committee agreed to make a final decision on the internal audit plan once further information was provided by CH on the proposed areas for review. | FARC | Cttee agreed areas for Internal Audit to review. These were presented to Board at May meeting and approved. Areas agreed: Risk management, Rent setting policy and IT Security. | Y | May
2021-02-03 | Internal Audit Update – Draft GDPR implementation plan The CHA DPO should be aware of the measures to be taken if a data breach occurs or if there is a Subject Access Request, and have processes in place to ensure that the organisation can react and meet reporting deadlines should the need arise. There is a need for higher level training but advised that, provided WMcC is aware of what actions must be taken in the event of a breach, this item could be removed from the outstanding actions schedule. RB agreed with this recommendation provided that the Committee was happy that any risk relating to the provision of training had been eliminated. | WMcC | Process flows have been prepared to document the Subject Access Request and Data Breach processes. Report from Internal Auditors confirm this as been implemented. | Y | 2021-05-01
2021-02-03 | Local Contractors - Accreditations and Qualifications It was agreed that WMcC should in the first instance contact the insurance broker to check exactly what CHA’s insurance does and does not cover. This matter should be raised at the February Board meeting. | WMcC | Broker stated that they expect us to confirm that any contractor appointed has valid insurance. Broker also noted that we have contingent cover for a situation when contractor did not have insurance or where their insurers did not accept liability. | Y | May
2021-02-03 | Landlord Responsibilities post Grenfell PF advised that work carried out on housing association properties in the past and signed off as acceptable based on custom and practice was now being revisited and rechecked. Some work that was initially deemed acceptable is now being questioned because it did not meet more stringent official standards and contractors are being told to rectify the situation. This relates not only to cladding but also fire escapes, fire doors etc. He asked if this recent development could have an impact on CHA and if there could be any risk to the organisation. He advised that landlords are expected to be much more attuned to what was deemed acceptable pre Grenfell and what is now acceptable post Grenfell. WMcC confirmed that Clanmil sub-contractors carry out regular fire risk assessments and he also referred to major remedial works carried out following an unfavourable fire risk inspection report from the Department back in 2014/15. He asked if, to provide additional assurance, CHA should appoint an independent consultant to inspect the buildings. RB suggested that NIFHA may be able to provide some guidance. | WMcC | I contacted both NIFHA and the Clanmil officer responsible for Statutory maintenance. They stated that the main impact of Grenfell was in relation to investigation of claddings used and in properties over 2 storeys high. Debbie Lyttle of Clanmil confirmed that CHA are fully compliant with all relevant regulations and are discharging their duties through inspections, including: Servicing fire alarms,fire equipment,emergency lighting and fire escapes. Regular fire risk assessments are performed and as good practice the Fire risk assessors now include an enhanced review of compartmentation within buildings, (which stems from Grenfell findings). | Y | May
2021-02-03 | Staffing Resources BR suggested that former CHA employees may currently be furloughed and could provide support in the interim. KB will follow up on this option. | KB | Former CHA employees are currently employed in permanent positions and are not currently furloughed | Y | Feb
2021-02-03 | Staffing Resources The Committee recommended that this matter is raised at the February board meeting to alert members to the risk and to highlight the difficulties in mitigating this risk. | WMcC | Matter was raised at Feb Board meeting. Board discussed various measures aimed at managing and reducing work load. | Y | Feb
2021-02-03 | Rent Increases Rent increases have to be approved by the Board before the Communities are informed so this subject must be discussed at the February Board meeting if deadlines are to be met. WMcC will prepare a paper for the February Board meeting. | WMcC | Proposed increases approved by Board. | Y | Feb

## Summary Updated Nov 2020 (hidden)
FARC Meetings - Summary of Action Points PAPER 2
Completed Actions marked in green
Date of FARC Meeting | Action Point | Responsible | Comments | Completed | Date
2020-08-07 | Matters Arising - COVID RB asked if CHA staff had been advised to download and use the COVID-NI app. He asked that this subject is added to the agenda for the upcoming Board meeting to get the views of members on use of the app and if it should be mandatory for staff. | WMcC | Added to the agenda and discussed at the Board meeting | y | August
2020-08-07 | CR2 - Failure to ensure appropriate standards of health and safety at CHA properties and those leased from CCT - COVID guidelines for landlords CK advised that there was a document published in July on the communities-ni.gov.uk website which may be useful and another on the hscni.net site relating to COVID for carers. She also mentioned that some organisations have carried out COVID training for staff and offered to provide further information on the courses and content. WMcC will review the available documents. | WMcC/CK | WMcC has reviewed relevant documents. Staff will check for Covid training. | Y | August
2020-08-07 | CR2 - Failure to ensure appropriate standards of health and safety at CHA properties and those leased from CCT & CR3 - Failure to maintain CHA properties to the required standards & CR9 - Impact of COVID-19 WMcC will add the COVID risks identified to the risk register under CR2, CR3 & CR9. - maintenance issues not being highlighted/addressed by the Communities due to COVID restrictions, the implication being that properties are not being maintained to the correct standard with the potential for health and safety issues. - the primary risk to CHA is an outbreak of COVID in one or more of the Communities which may be as a result of insufficient measures in place at the Community to mitigate the risk of infection - CHA must protect its tenants and there is a risk that “the Association fails to ensure that Communities follow statutory guidance relating to COVID control”. The implication is an infection breakout at one or more of the Communities. | WMcC | Risk register has been updated | Y | September
2020-08-07 | CR5 - Failure to achieve necessary standards of governance RB advised that the risk “unfavourable outcome of DfC RSAR” should actually be an implication. WMcC will amend the Risk Register accordingly. | WMcC | Risk register has been updated | Y | September
2020-08-07 | CR8 - Loss of Strategic Direction RB advised that an implication under CR8 should be that “the future of CHA is determined by a third party with the potential of risk to the Community life sharing culture”. | WMcC | Risk register has been updated | Y | September
2020-08-07 | CR9 - Impact of COVID-19 RB advised that CHA must rely on their managing agents to have controls in place to mitigate the risk of COVID. Until CHA can be certain of the extent to which the controls are adequate both the inherent and residual risks should be raised. | WMcC | Risk register has been updated | Y | September
2020-08-07 | Update of Long Term Financial Plan (paper 5) WMcC advised that cash flows are available and he reported that over the next 4 years the cash balance goes from £1.4m to £1.33m. He agreed to send details of the cash flow for the next 3 year period to PF for review. | WMcC/PF | The detailed excel spreadsheets were sent to Paddy on 2nd November. | Y | November
2020-08-07 | Update of Long Term Financial Plan (paper 5) RB stated that the LTFP must be reviewed and approved by the Board before being sent to Jonathan Boggs. He instructed WMcC to prepare a document to present to the Board with sufficient information for members to approve and forward on to Jonathan Boggs. The report should include this issues that have just been discussed including Ciaran/Colman and the level of cash reserves going forward and should also highlight how the new plan differs from the original. | WMcC/PF | WMcC prepared and presented paper to Board at August meeting. LTFP was approved. | Y | August
06/08/2018 & 27/03/20 | Review of the Risk Register and Action Plan JN raised concerns over the lack of a business continuity plan. This subject is covered in the action plan under CR4 (failure to achieve appropriate standards of operational control) with a target completion date of 30/9/18. JC advised that he has already instigated discussions with the Communities on this subject. He stated that the drafting of business continuity plans is extremely complex because of the Camphill/CHA inter-relationship and shared facilities at the Camphill sites. There is a lot of investigative work involved and the co-operation of the Communities is essential. CH offered to supply an example of a Business Continuity Plan to facilitate the drafting process. RB requested that the need for a location specific BCP is considered in light of the model BCP provided by ASM. | WMcC/CH | WMcC has contacted each Community requesting sight of their BCPs. All have confirmed they will share these. Glencraig are currently in the process of developing their plan. CH provided examples of BCPs for consideration . CHA staff will develop in line with Community plans. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan WMcC should attend a GDPR training session and the DPO should receive a more structured higher level training to cover case law etc. | WMcC/KB | WMcC attended a GDPR awareness workshop in June 2019. Training material has been sent to ASM for review Sept 19. The need for further training is to be clarified. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan CH recommended that it would be prudent to seek legal advice in relation to GDPR requirements on tenancy agreements and JMAs. | WMcC/KB | New tenancy agreements for MG and Clanabogan have been drafted,agreed with CH and forwarded to Communities for signing. Glencraig tenancy arrangements/GDPR to be discussed with Paul Betts |  | on going

## Summary updated Jan 2021 (hidden)
FARC Meetings - Summary of Action Points PAPER 2
Completed Actions marked in green
Date of FARC Meeting | Action Point | Responsible | Comments | Completed | Date
2020-11-04 | WMcC stated that the final actions required to achieve full compliance with GDPR are close to completion and it would be helpful to arrange for M McNeice(ASM) to provide support to finalise these. | WMcC | WMcC and MMcN had arranged to meet in January but the lateset covid lockdown has put this back. It is planned for this to take place in mid March(covid allowing). | o/s
2020-11-04 | There are no Tenancy agreements in place for Glencraig. WMcC was asked to follow this up with Paul Betts(CEO Glencraig) and if necessary check with Jenny Ebbage. | WMcC | WMcC discussed with PB who was unaware of the situation and whether these were relevant for Glencraig. PB agreed to investigate this and to revert to WMcC. WMcC is arranging a meeting in mid February between the Chair of CHA,Chair of Glencraig, PB and himself, and he will add this issue to the agenda. | o/s
2020-11-04 | WMcC to raise the matter of the recent Ministerial statement regarding possible changes to the Housing Executive with A Hamilton to consider informing Board members. | WMcC | AH agreed that a copy of the Minister's statement be attached to the next Board meeting papers for member's information. | Y | 2020-11-11
2020-11-04 | Review of the Risk Register and Action Plan The following amendments were made to the risk register after review by members: CR2 - A control was added stating that the Communities are now permitting outside contractors to enter properties to complete remedial works subject to the use of the correct PPE and adherence to social distancing regulations. CR4 - The control relating to VfM should be amended to reflect that the VfM statement has now been approved by the Board. CR8 - Another element should be added to this risk stating that the proposed way forward may not be consistent with legislation, and a control added that clarification of the legal feasibility has been sought from the Department's legal advisers. | WMcC | Risk Register has been updated. | Y | 2021-01-29
06/08/2018 & 27/03/20 | Review of the Risk Register and Action Plan JN raised concerns over the lack of a business continuity plan. This subject is covered in the action plan under CR4 (failure to achieve appropriate standards of operational control) with a target completion date of 30/9/18. JC advised that he has already instigated discussions with the Communities on this subject. He stated that the drafting of business continuity plans is extremely complex because of the Camphill/CHA inter-relationship and shared facilities at the Camphill sites. There is a lot of investigative work involved and the co-operation of the Communities is essential. CH offered to supply an example of a Business Continuity Plan to facilitate the drafting process. RB requested that the need for a location specific BCP is considered in light of the model BCP provided by ASM. | WMcC/CH | WMcC has contacted each Community requesting sight of their BCPs. All have confirmed they will share these. Glencraig are currently in the process of developing their plan. CH provided examples of BCPs for consideration . CHA staff will develop in line with Community plans. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan WMcC should attend a GDPR training session and the DPO should receive a more structured higher level training to cover case law etc. | WMcC/KB | WMcC attended a GDPR awareness workshop in June 2019. Training material has been sent to ASM for review Sept 19. The need for further training is to be clarified. |  | on going
2018-04-30 | Internal Audit Update – Draft GDPR implementation plan CH recommended that it would be prudent to seek legal advice in relation to GDPR requirements on tenancy agreements and JMAs. | WMcC/KB | New tenancy agreements for MG and Clanabogan have been drafted,agreed with CH and forwarded to Communities for signing. Glencraig tenancy arrangements/GDPR to be discussed with Paul Betts |  | on going

## Summary updated August 2024
Planning Committee - Summary of o/s Action Points PAPER 1A
Completed Actions marked in green
Point | Date of PC Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2025-06-11 | Business Plan Monitoring WMcC to update draft report to: shorten report, add column reference to appendices, consider metrics to apply, and show projected completion dates, and send to Members for consideration at next cttee meeting for Members review. | WMcC | Draft has been amended, Paper 2A notes proposed amendments. | Y | 2025-08-20
2 | 2025-06-11 | Annual report 2024-25 WMcC was asked to include a short article in the Annual Report reporting achievements and resident experiences based upon a significant planned maintenance project completed in the year. | WMcC | A short article prepared by Michael on the replacement of old wooden windows and doors at Mourne Grange house with modern pvc and in keeping with the "old" style was included in the Annual Report. | Y | 2025-06-13
3 | 2025-06-11 | Decent home standard Staff have been asked to develop a CHA specific decent home standard, taking account of relevant health and safety , energy efficiency, and accessibility , as well as the various issues included in the current DfC standard. | All Staff | Work is underway to develop our own standard, but there has been no movement/progress from the department to report. |  | 2026-03-04
4 | 2025-06-11 | 5 Year improvement plan Staff have been asked to select 2 properties and draft a 5 year improvement plan to include the issues considered in the DHS discussions. | All Staff | We prepared a 5 year plan for Novalis from Glencraig and Fairy Grove from Mourne Grange attached at Papers 3A & 3B.. | Y | 2025-08-20

## Summary (hidden)
FARC Meetings - Summary of Action Points PAPER 2
Completed Actions marked in green
| Date of FARC Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2019-03-27 | CH offered to supply an example of a Business Continuity Plan to facilitate the drafting process. RB requested that the need for a location specific BCP is considered in light of the model BCP provided by ASM. | CH | CH advised at the June FARC that an example was currently being prepared and would be supplied in due course |  | on going
2 | 2018-08-06 | Review of the Risk Register and Action Plan JN raised concerns over the lack of a business continuity plan. This subject is covered in the action plan under CR4 (failure to achieve appropriate standards of operational control) with a target completion date of 30/9/18. JC advised that he has already instigated discussions with the Communities on this subject. He stated that the drafting of business continuity plans is extremely complex because of the Camphill/CHA inter-relationship and shared facilities at the Camphill sites. There is a lot of investigative work involved and the co-operation of the Communities is essential. | WMcC/KB/BS |  |  | on going
3 | 2018-04-30 | Internal Audit Update – Draft GDPR implementation plan GDPR Project Plan - A timebound project plan is required to set out how the organisation intends to achieve compliance. | WMcC/KB | Plan will be developed with assistance from ASM. A review of progress was carried out on 12th September and ASM are currently reviewing documentation provided, actions completed and actions outstanding. |  | on going
4 | 2018-04-30 | Internal Audit Update – Draft GDPR implementation plan WMcC should attend a GDPR training session and the DPO should receive a more structured higher level training to cover case law etc. | WMcC/KB | WMcC attended a GDPR awareness workshop in June 2019. Training material has been sent to ASM for review Sept 19. The need for further training is to be clarified. |  | on going
5 | 2018-04-30 | Internal Audit Update – Draft GDPR implementation plan CH recommended that it would be prudent to seek legal advice in relation to GDPR requirements on tenancy agreements and JMAs. | WMcC/KB | New tenancy agreements for MG and Clanabogan have been drafted,agreed with CH and forwarded to Communities for signing. Glencraig tenancy arrangements/GDPR to be discussed with Paul Betts |  | on going
6 | 2019-03-27 | Rent setting AH asked WMC to look again at the inflation rate as close as possible to the time of the rent setting process to provide evidence to back up any requested housing benefit increase and suggested that talking to other housing associations could also be helpful. | WMcC | I had contacted NIHE regarding rent increases in MG and Clan of 1.9%. I prepared increase letters and confirmed with AH before sending these to communities. AH instructed me to hold off sending rent increase letters as the increase would need to be formally approved by the Board.
7 | 2019-06-19 | Treasury Policy RB to liaise with WMcC to amend policy in line with cttee discussions. | RB/WMcC |  | Y | 2019-07-01
8 | 2019-06-19 | Review of Risk Register CR3 Add risk of Clanmil withdrawing maintenance service CR4 Delete action planned to visit other HAs in GB & Ireland CR5 Approval of RSAR is not responsibility of FARC, this should be approved by Board. WMcC to discuss with Chair possibly holding a Special Board Meeting for this purpose. | WMcC |  | Y | 2019-06-01
9 | 2019-06-19 | WMcC to raise the issue of amending the wording of notes 19 and 21 in Financial Statements with the Auditors as outlined by FARC members. | WMcC |  | Y | 2019-06-01
10 | 2019-06-19 | RB asked WMcC to convey to the external auditors the Committee’s disappointment at the delay in the accounts. | WMcC |  | Y | 2019-06-01
11 | 2019-03-27 | WMcC’s performance review to be completed by the end of April. | AH/WMcC |  | Y | 2019-07-25
12 | 2018-11-07 | WMcC to prepare a letter of authorisation for the bank and draft a paper concerning on-line banking for presentation to the Board. | WMcC | WMcC/KB met Bank official to prepare for proposals to present to Board | Y | 2019-06-01
13 | 2018-08-06 | Internal Audit Update – Financial Management WMcC agreed to look at Bankline, or a similar electronic banking system. | WMcC |  | Y | 2019-06-01
14 | 2018-08-06 | GDPR - Data Requests There is a requirement to identify what data is held by CHA and where/how this data is held. JC confirmed that a data inventory is yet to be prepared. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01
15 | 2018-08-06 | Review of the Risk Register and Action Plan RB referred to the requirement for a procurement policy against risk CR4. WMcC agreed to draft the policy. | WMcC | Policy has been prepared and will be presented to FARC in June | Y | 2019-06-01
16 | 2018-04-30 | Internal Audit Update – Draft GDPR implementation plan Responding to data requests There is a need to prepare a data inventory to identify what information is held by CHA and how/where this data is held. | WMcC/KB | Work on data inventory document is complete | Y | 2019-09-01