## Outstanding Items
Board Meetings - Summary of o/s Action Points PAPER 2
Completed Actions in green
Item ref | Date of Board Meeting | Action Point | Responsible | Comments | Completed | Date
1 | 2023-08-23 | GDPR Refresher training WMcC was asked to source training for both Members and staff on GDPR. | WMcC | At the Board meeting on 23 October 2024 Members agreed that on-line training would be appropriate for their requirements. MMcA had recent experience of on-line GDPR training and forwarded details to WMcC. This has now been arranged, details attached at Paper 2B. | Y | 2024-12-31
2 | 2023-12-13 | Board refreshment It was noted that efforts should be continued to secure Tenant representation from Clanabogan and also seek finance/accountancy experience. | LD | LD has raised this issue at Camphill Northern Neighbourhood meetings and other avenues are also being actively followed up. | ongoing | Target 31/12/24
3 | 2024-04-24 | Glencraig occupancy WMcC to follow up on obtaining the additional occupancy information requested from Glencraig. | WMcC | We have now received all the information requested and agreed this will be updated quarterly. | Y | Target 31/10/24
4 | 2024-10-23 | Decent Homes Standard WMcC was asked to keep Board Members updated on DfC review of the Decent Homes Standard and of relevant developments in England.. | WMcC | To date I have nothing to report. | ongoing | Target 31/3/25
5 | 2024-10-23 | Website development WMcC was asked to take forward the development of a website for the Association. | SL/WMcC | SL has developed a "first draft" website which we aim to upload before the target date. | ongoing | Target 31/12/24
6 | 2024-10-23 | Letter to Nigel Carson WMcC was asked to draft a letter to thank Nigel for his assistance in developing the Corporate Strategy. | WMcC | Letter sent and response ffrom Nigel forwarded to Members. | Y | Target 30/11/24